## New Text Document
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Notes | Date started (actual date) | Date finished (actual date)
0 | Login Functionality | As a user, I want to log in with identical ID and password so that I can access my account and save personal info. | high | 1 | 1. User can log in with correct ID and password. 2. User can create an account with unique ID and password. 3. User can view and edit their personal profile. |  | 2024-03-15 | 2024-03-20
1 | Login Testing | As a developer, I want to test some weird ID and password cases so that I can ensure the robustness of the login system. | mid | 1 | 1. Test various combinations of ID and password. 2. Identify and document any bugs found. 3. Submit a report of the test results. |  | 2024-03-20 | 2024-03-22
2 | Parent-Child Accounts | As a parent, I want to create parent and children accounts so that I can manage my children's accounts and monitor their activities. | mid | 1 | 1. Ability to select a role (parent/child) during account creation. 2. Parental controls to manage children's accounts. |  | 2024-03-15 | 2024-03-20
3 | Transaction Tracking | As a user, I want my transactions to be tracked and output as a file so that I can keep a record of all financial activities. | mid | 1 | 1. Transaction history is stored and can be output as a file. 2. The output file is saved to the local disk. |  | 2024-03-15 | 2024-03-20
4 | Account Information Storage | As a user, I want to store the main info about my account so that I can perform financial transactions like top-ups and withdrawals. | high | 1 | 1. Account information is stored securely. 2. Top-up and withdraw functions work properly. |  | 2024-03-15 | 2024-03-20
5 | Setting Savings Goals | As a parent, I want to set goals for my children to save money so that I can encourage financial discipline and savings habits. | high | 1 | 1. Ability to set savings goals with an amount and deadline. 2. Children's accounts can view the added goals. |  | 2024-03-15 | 2024-03-20
6 | Password Change | As a user, I want to change my password so that I can maintain the security of my account. | mid | 1 | 1. User can authenticate using personal info to change the password. 2. System does not reveal the old password. |  | 2024-03-15 | 2024-03-20
7 | Password Hashing | As a developer, I want to use hash to store passwords so that the safety and security of user data is ensured. | low | 2 | 1. Passwords are stored as hash codes for security. 2. Hashing algorithm is implemented correctly. |  | 2024-03-20 | 2024-03-31
8 | Graphical User Interface (GUI) | As a user, I want a GUI so that I can easily interact with the software and perform all the above functions. | high | 2 | 1. GUI is user-friendly and accessible to children. 2. All functionalities are accessible through the GUI. |  | 2024-04-01 | 2024-05-01
9 | Virtual Currency Transfer | As a user, I want to transfer virtual currency so that I can share and manage finances within the family. | high | 2 | 1. Users can input numbers to make a transfer. 2. Transfer is recorded and can be viewed by all parties. |  | 2024-04-01 | 2024-05-01
10 | Family Group Savings | As a family, I want to form groups to save money together so that we can pool resources and achieve financial goals. | mid | 2 | 1. Ability to create and join family groups. 2. Group members can see each other's contributions and savings goals. |  | 2024-04-01 | 2024-05-01
11 | Demand and Fixed Deposits | As a user, I want to have both demand (checking) and fixed (time) deposit accounts so that I can manage my funds with different accessibility and profit options. | high | 3 | 1. Demand deposit should allow for immediate access to funds with no interest. 2. Fixed deposit should allow for setting a deposit amount and a fixed term. 3. Fixed deposit should accrue interest over the term. 4. At the end of the term, the principal and interest should be transferred to the demand deposit account. 5. Users should be able to view the status and details of all their deposits. |  | 2024-05-01